## Overview
Meridian Car Rentals Analytics Platform
Domain: Car Rental / Fleet & Booking Operations Analytics (multinational, multi-branch)
Objective Summary
Meridian Car Rentals needs a single, trustworthy data platform that continuously ingests its five operational data sources (customer records, fleet inventory, billing & payments, booking transactions, and vehicle telematics), cleans and validates that data with visible data-quality checks, and delivers the result through an Executive Dashboard and an Operational Dashboard -- built on Microsoft Fabric's Lakehouse medallion architecture (Bronze/Silver/Gold), promoted safely across DEV, UAT, and PROD environments. This work plan breaks that build into six phases, from requirements and architecture through ingestion, transformation, orchestration, dashboarding, and final promotion/handover.
Phase Summary
Phase | Focus Area | Key Deliverable
1 | Requirements, Architecture & Data Model Design | Business Requirements Document, Architecture Blueprint (workspace layout, medallion flow, source-to-landing mapping), draft data model
2 | Batch & Streaming Ingestion, Environment Configuration | Working batch ingestion for all three file-based sources; working streaming ingestion into Bronze for both event sources; environment configuration approach documented
3 | Bronze/Silver/Gold Transforms & Data Quality | Silver-layer cleansed data for all five sources, documented data quality checks with results, Gold-layer business-ready tables/model
4 | Orchestration, Monitoring & Dashboard Start | End-to-end orchestrated pipeline with monitoring/alerting; first working drafts of both dashboards
5 | Finish Dashboards, Testing & Validation Against Success Criteria | Finished, tested dashboards; completed success-criteria validation checklist with evidence
6 | Environment Promotion, Documentation & Final Presentation | Solution deployed and verified across DEV -> UAT -> PROD, complete documentation package, final presentation/demo

## Workplan
# | Phase | Task | Description | Est Days | Owner | Dependency | Priority
1.1 | 1 | Review client request & confirm understanding | Review the client request and confirm your understanding of Meridian's business challenges, objectives, and success criteria. | 0.5 | All | None | Must
1.2 | 1 | Run mock requirements workshop | Translate the business challenges into concrete business questions (e.g., "which branches are under-using their fleet?", "how much revenue are we losing to late returns?"). | 1 | Business Analyst | 1.1 | Must
1.3 | 1 | Design target architecture | Name your three Fabric workspaces (dev/uat/prod), plan your lakehouse(s) and medallion zones, and sketch how each of the five sources lands in Bronze. | 1.5 | Data Architect | 1.1 | Must
1.4 | 1 | Design data model | Identify the business entities (customers, vehicles, branches, bookings, payments, telematics readings) and how they relate. Decide your Silver/Gold table structure and grain for each entity. | 1.5 | Data Architect | 1.2 | Must
1.5 | 1 | Confirm PII fields & governance needs | Confirm which fields are PII and note where masking/governance controls will be needed. | 0.5 | Data Architect | 1.4 | Should
2.1 | 2 | Stand up three Fabric workspaces | Stand up your three Fabric workspaces (dev/uat/prod) and agree on a naming convention for lakehouses, e.g. lh_carrental_bronze, lh_carrental_silver, lh_carrental_gold. | 1 | Platform Engineer | 1.3 | Must
2.2 | 2 | Build batch ingestion: Fleet Inventory & Billing | Build batch ingestion for Fleet Inventory and Billing & Payments from cloud file storage into the Bronze lakehouse (Fabric Data Factory pipeline, scheduled hourly and daily respectively). | 1.5 | Data Engineer | 2.1 | Must
2.3 | 2 | Build batch ingestion: Customer Master Data | Build batch ingestion for Customer Master Data from the document library drop into the Bronze lakehouse (scheduled weekly). | 1 | Data Engineer | 2.1 | Must
2.4 | 2 | Configure Eventstream for Booking & Telematics | Configure a Fabric Eventstream to consume the Booking Transactions and Telematics live event streams (from the Kafka-style streaming source) and land raw events into the Bronze lakehouse (directly, or via a KQL database staging step first). | 1 | Data Engineer | 2.1 | Must
2.5 | 2 | Parameterize environment configuration | Confirm environment-specific configuration (connection strings, credentials, workspace IDs) is parameterized so the same pipeline logic can be promoted across dev/uat/prod later. | 0.5 | Platform Engineer | 2.2, 2.3, 2.4 | Should
3.1 | 3 | Build Silver-layer notebooks/pipelines | Build Silver-layer notebooks/pipelines that clean, standardize, and validate each of the five sources (deduplication, type enforcement, referential checks against customer/vehicle/branch identifiers, handling of late-arriving or malformed records). | 2 | Data Engineer | 2.2, 2.3, 2.4 | Must
3.2 | 3 | Implement data quality framework | Define checks (completeness, uniqueness, valid ranges/enums, referential integrity) and make pass/fail results visible, not silent. | 1.5 | Data Engineer | 3.1 | Must
3.3 | 3 | Build Gold-layer tables | Build Gold-layer tables that answer the business questions identified in Phase 1 (fleet utilization, booking performance, revenue per vehicle, customer value, late returns, maintenance/telematics alerts, suspected fraud) at the grain appropriate to each subject area. | 1 | Data Engineer | 3.1 | Must
3.4 | 3 | Apply PII handling in Silver/Gold | Apply appropriate handling for PII fields consistent with your Phase 1 governance notes. | 0.5 | Data Engineer | 1.5, 3.1 | Must
4.1 | 4 | Wire full pipeline orchestration | Wire the full pipeline together with Fabric Data Factory orchestration: batch schedules (hourly/daily/weekly) trigger the right notebooks/pipelines in the right order; streaming ingestion runs continuously. | 1.5 | Platform Engineer | 3.3 | Must
4.2 | 4 | Add monitoring & failure alerting | Add monitoring and failure alerting (pipeline run failures, data quality check failures, streaming ingestion gaps). | 1 | Platform Engineer | 4.1 | Should
4.3 | 4 | Start Executive Dashboard | Begin building the Executive Dashboard in Power BI on top of the Gold semantic model: top-line KPIs, trend views, executive summary layout. | 1.5 | BI Developer | 3.3 | Must
4.4 | 4 | Start Operational Dashboard | Begin building the Operational Dashboard: operational fleet/booking metrics, exception views for things needing attention. | 1 | BI Developer | 3.3 | Must
5.1 | 5 | Complete both dashboards | Ensure the Executive Dashboard supports leadership-level review and cross-region performance comparison, and the Operational Dashboard supports drill-down from summary to branch/vehicle/booking level plus exception reporting. | 2 | BI Developer | 4.3, 4.4 | Must
5.2 | 5 | Test pipeline end-to-end | Re-run batch loads, replay/produce streaming events, and confirm Gold data and dashboards update correctly. | 1.5 | QA / Tester | 4.1, 5.1 | Must
5.3 | 5 | Validate against success criteria | Validate the solution against every measurable success criterion in the client request (Section 4): refresh cadence per source, reporting turnaround, data quality visibility, dashboard usability, environment promotion path. | 1 | All | 5.2 | Must
5.4 | 5 | Fix gaps found during validation | Fix gaps found during validation. | 0.5 | All | 5.3 | Must
6.1 | 6 | Promote DEV -> UAT -> PROD | Promote the solution from the DEV workspace to UAT using Fabric deployment pipelines; run UAT verification; promote to PROD. | 1.5 | Platform Engineer | 5.4 | Must
6.2 | 6 | Verify promoted PROD pipeline | Confirm the promoted PROD pipeline runs correctly against production-equivalent configuration (schedules, connections, Eventstream). | 1 | Platform Engineer | 6.1 | Must
6.3 | 6 | Finalize documentation | Finalize documentation: architecture, data dictionary, data quality rules, orchestration schedule, runbook for operating and monitoring the platform, and known limitations. | 1.5 | All | 6.2 | Must
6.4 | 6 | Prepare & deliver final presentation | Prepare and deliver the final stakeholder presentation and live demo, showing the platform working end-to-end and mapping the result back to Meridian's original business challenges and success criteria. | 1 | All | 6.3 | Must