## Overview
Credit Risk & Portfolio Analytics
Meridian Trust Bank — Retail Banking / Credit Risk domain
Objective
Design and build an end-to-end Microsoft Fabric data platform that ingests Meridian Trust Bank's batch data (loan applications, loan repayments, weekly credit bureau reports) and real-time data (customer transactions, market indicators), organizes it through a governed Bronze/Silver/Gold medallion architecture with automated data quality checks, and delivers an Executive Dashboard and a Risk & Operations Dashboard — promoted through DEV, UAT, and PROD Fabric workspaces via a repeatable deployment pipeline — so the bank can answer default-rate, exposure, profitability, and delinquency questions on demand instead of through manual spreadsheet reporting.
Phase-by-Phase Summary
Phase | Focus Area | Key Deliverable
Phase 1 | Requirements, Architecture & Data Model Design | Requirements confirmation notes, architecture diagram, draft data model (fact/dimension design), three Fabric workspaces provisioned.
Phase 2 | Batch & Streaming Ingestion, Environment Configuration | Working batch ingestion pipelines for all 3 batch sources, working Eventstream ingestion for both streaming sources, Bronze lakehouse populated, environment configuration documented.
Phase 3 | Bronze -> Silver -> Gold, Data Quality & Transformations | Silver layer with documented cleansing/DQ rules, DQ results log/report, Gold-layer star schema populated, sample validation queries.
Phase 4 | Orchestration, Monitoring & Dashboard Build (Start) | End-to-end orchestrated pipeline, monitoring/alerting in place, Executive Dashboard first draft.
Phase 5 | Finish Dashboards, Testing & Validation | Both dashboards complete, end-to-end test results, success-criteria validation checklist, UAT sign-off notes.
Phase 6 | Deployment (DEV -> UAT -> PROD), Documentation & Presentation | Solution promoted through DEV/UAT/PROD via Fabric deployment pipelines, complete documentation set, final presentation delivered.

## Workplan
# | Phase | Task | Description | Est Days | Owner | Dependency | Priority
1.1 | Phase 1 | Confirm scope & success criteria | Read the client request end-to-end; confirm the two required dashboards (Executive, Risk & Operations) and the measurable success criteria with your instructor acting as client proxy. | 1 | Business Analyst | None | Must
1.2 | Phase 1 | Confirm data sources & arrival mechanics | Confirm the five data sources and how each will physically arrive: Loan Applications (daily batch CSV), Loan Repayments (daily batch CSV), Credit Bureau Reports (weekly CSV/XML to a shared document library), Customer Transactions (real-time stream), Market Data (real-time stream). | 1 | Data Architect | 1.1 | Must
1.3 | Phase 1 | Produce architecture diagram | Produce a high-level architecture diagram: sources -> landing/ingestion -> Bronze -> Silver -> Gold -> Power BI, showing Data Factory pipelines for batch, Eventstream for streaming, and the three-workspace DEV/UAT/PROD promotion path. | 2 | Data Architect | 1.2 | Must
1.4 | Phase 1 | Design star schema (fact/dimension model) | Design your own star schema (fact and dimension tables) to answer the business questions in the client request (default rate trending, non-performing exposure, portfolio profitability, delinquency drill-down). Derive it from the business questions and available fields, do not assume a schema. | 2 | Data Architect | 1.1 | Must
1.5 | Phase 1 | Provision Fabric workspaces | Set up the three Fabric workspaces (CreditRisk-DEV, CreditRisk-UAT, CreditRisk-PROD) and assign them to a capacity. | 1 | Data Engineer | None | Must
2.1 | Phase 2 | Build batch ingestion for Loan Applications & Repayments | Build Fabric Data Factory pipelines (Copy activities) to land the two S3 batch sources - Loan Applications and Loan Repayments - into lh_creditrisk_bronze, on a daily schedule. | 3 | Data Engineer | 1.5 | Must
2.2 | Phase 2 | Build ingestion path for Credit Bureau Reports | Build the ingestion path for Credit Bureau Reports from the simulated SharePoint document library into lh_creditrisk_bronze, on a weekly schedule. | 2 | Data Engineer | 1.5 | Must
2.3 | Phase 2 | Set up streaming Eventstreams | Set up a Fabric Eventstream for each streaming source (Customer Transactions, Market Data), consuming from the Upstash Kafka topics and landing events into Bronze (directly, or via a KQL database first for queryable hot storage). | 3 | Data Engineer | 1.5 | Must
2.4 | Phase 2 | Configure environment-specific connections | Configure environment-specific connections/credentials for DEV (S3 read credentials, SharePoint/library path, Kafka bootstrap/credentials) so pipeline logic can later be promoted to UAT and PROD with environment-specific parameters. | 1 | DevOps/Platform Engineer | 2.1; 2.2; 2.3 | Should
3.1 | Phase 3 | Build Silver-layer cleansing/standardization | Build Silver-layer notebooks/pipelines: cleanse and standardize each source (data types, deduplication, null handling, standardizing status/category values), conform customer and loan identifiers across sources. | 4 | Data Engineer | 2.1; 2.2; 2.3 | Must
3.2 | Phase 3 | Implement data quality framework | Implement a data quality framework applied at Bronze->Silver: completeness checks, valid-range checks (e.g., credit score bounds, non-negative amounts), referential integrity checks (repayments reference existing loans/customers), with failed records logged/quarantined rather than dropped silently. | 3 | Data Engineer | 3.1 | Must
3.3 | Phase 3 | Build Gold layer star schema | Build the Gold layer: populate your fact and dimension tables from Phase 1's data model, ready to answer the business questions from the client request. | 3 | Data Engineer | 3.1; 1.4 | Must
3.4 | Phase 3 | Validate Gold layer with sample queries | Validate the Gold layer with sample queries against the actual business questions (e.g., "defaults trend over the last 12 months," "where is non-performing exposure concentrated"). | 1 | BI Developer | 3.3 | Should
4.1 | Phase 4 | Orchestrate end-to-end pipelines | Wire all pipelines (batch ingestion, streaming ingestion checks, Bronze->Silver->Gold transforms) together into orchestrated Fabric Data Factory pipelines with proper scheduling and dependency ordering. | 2 | Data Engineer | 3.2; 3.3 | Must
4.2 | Phase 4 | Add monitoring & alerting | Add basic monitoring: pipeline run history/alerts on failure, and a simple view of data quality pass/fail rates over time. | 2 | Data Engineer | 4.1 | Should
4.3 | Phase 4 | Start Executive Dashboard | Begin building the Executive Dashboard in Power BI on top of the Gold semantic model: headline KPIs, trend visuals, and an executive summary view. | 3 | BI Developer | 3.3 | Must
5.1 | Phase 5 | Complete both dashboards | Complete the Executive Dashboard and build the Risk & Operations Dashboard: detailed operational metrics, drill-down from portfolio/segment to individual loan/customer, and exception/outlier reporting for loans and customers needing attention. | 4 | BI Developer | 4.3 | Must
5.2 | Phase 5 | Run end-to-end testing & validation | Run end-to-end testing of the full pipeline (batch and streaming) and validate results directly against the client's measurable success criteria (ingestion latency, DQ pass rate, dashboard responsiveness, drill-down capability). | 2 | QA/Test Lead | 4.1; 5.1 | Must
5.3 | Phase 5 | Conduct UAT walkthrough | Conduct a UAT walkthrough of both dashboards against the client's stated business questions and success criteria; capture and address any gaps. | 1 | All | 5.1; 5.2 | Must
6.1 | Phase 6 | Promote DEV -> UAT -> PROD | Use Fabric deployment pipelines to promote the validated solution from CreditRisk-DEV -> CreditRisk-UAT -> CreditRisk-PROD, updating environment-specific parameters (connections, credentials, schedules) at each stage. | 2 | DevOps/Platform Engineer | 5.2; 5.3 | Must
6.2 | Phase 6 | Re-validate in UAT and PROD | Re-run validation in UAT and PROD to confirm the promoted solution behaves the same as DEV. | 1 | QA/Test Lead | 6.1 | Must
6.3 | Phase 6 | Finalize documentation | Finalize documentation: architecture, data dictionary/data model, data quality rules, orchestration/runbook, and environment promotion process. | 2 | All | 6.1 | Must
6.4 | Phase 6 | Deliver final presentation | Prepare and deliver the final presentation/demo to the client (instructor acting as client proxy), covering the architecture, the two dashboards, and how each success criterion was met. | 1 | All | 6.2; 6.3 | Must