## Overview
Patient Care & Hospital Operations Analytics Platform
Domain: Healthcare / Hospital Operations — Meridian Health Network
Objective
Design and build an end-to-end Microsoft Fabric analytics platform that integrates five batch sources (EHR, Billing & Claims, Pharmacy Inventory, Bed Occupancy, and Hospital Staff Scheduling via SharePoint) and two streaming sources (Patient Vitals Monitoring and Prescriptions via Kafka) through a governed Bronze/Silver/Gold medallion architecture, culminating in an Executive Dashboard and an Operational/Clinical Dashboard in Power BI, promoted through DEV/UAT/PROD workspaces with documented data quality, orchestration, monitoring, and PII/PHI governance controls.
Phase-by-Phase Summary
Phase | Focus Area | Key Deliverable
Phase 1 | Requirements, Architecture & Data Model Design | Requirements/KPI document, draft fact/dimension data model, end-to-end architecture diagram, and Fabric three-workspace plan.
Phase 2 | Batch + Streaming Ingestion, Environment Config | Working batch ingestion for all 5 batch sources and Eventstream ingestion for both streaming sources, all landing in the DEV Bronze lakehouse.
Phase 3 | Bronze / Silver / Gold, Data Quality, Transformations | Silver and Gold lakehouses populated end-to-end for a full batch cycle plus a running streaming window, with documented, automated data quality checks and visible results.
Phase 4 | Orchestration, Monitoring & Start Dashboards | End-to-end orchestrated pipeline (Data Factory) with failure/DQ monitoring, and a first working draft of the Executive Dashboard.
Phase 5 | Finish Dashboards, Testing, Validate Against Success Criteria | Both dashboards complete, end-to-end test results (including a deliberately broken case), and a completed success-criteria validation checklist.
Phase 6 | Deploy DEV/UAT/PROD, Documentation, Final Presentation | Promoted PROD workspace via Fabric deployment pipelines, final documentation package, and final presentation to leadership.

## Workplan
# | Phase | Task | Description | Est Days | Owner | Dependency | Priority
1.1 | Phase 1 | Derive KPI / requirements document | Re-read client-request.md and turn the business questions into a concrete list of KPIs and metrics (wait times, bed occupancy, readmission rate, staffing ratios, claim denial rate, ALOS, critical-alert rate, drug stockout frequency, etc.) — derive your own formulas, don't guess at 'the' answer. | 1 | BI Developer | None | Must
1.2 | Phase 1 | Design target data model | Identify facts and dimensions, the grain of each fact, and the relationships between patients, staff, facilities, claims, prescriptions, and vitals. | 1 | Data Architect | 1.1 | Must
1.3 | Phase 1 | Produce architecture blueprint | Document the full path from source to dashboard: batch sources -> Bronze -> Silver -> Gold -> Power BI, and streaming sources -> Eventstream -> Bronze -> Silver -> Gold -> Power BI. | 1 | Data Architect | 1.2 | Must
1.4 | Phase 1 | Document three-workspace strategy | Decide and document the DEV/UAT/PROD Fabric workspace strategy per the framework convention (naming, promotion approach). | 0.5 | Platform Engineer | 1.3 | Must
1.5 | Phase 1 | Compile Phase 1 deliverables package | Assemble the requirements/KPI document, draft data model sketch, architecture diagram, and Fabric workspace plan into a reviewable package. | 0.5 | All | 1.1, 1.2, 1.3, 1.4 | Should
2.1 | Phase 2 | Stand up Fabric workspaces & Bronze lakehouses | Create the three Fabric workspaces (DEV/UAT/PROD) and a Bronze lakehouse in each, per the naming convention. | 1 | Platform Engineer | 1.4 | Must
2.2 | Phase 2 | Build ingestion for 4 S3 batch sources | Build ingestion for EHR, Billing & Claims, Pharmacy Inventory, and Bed Occupancy from AWS S3, using credentials/bucket details from the instructor. | 2 | Data Engineer | 2.1 | Must
2.3 | Phase 2 | Build ingestion for SharePoint staff scheduling source | Build ingestion for Hospital Staff Scheduling from the simulated SharePoint document library. | 1 | Data Engineer | 2.1 | Must
2.4 | Phase 2 | Build Eventstream ingestion for streaming sources | Set up the Upstash Kafka connection and build a Fabric Eventstream for each streaming source (Patient Vitals Monitoring, Prescriptions), landing into Bronze directly or via a KQL database. | 1.5 | Data Engineer | 2.1 | Must
2.5 | Phase 2 | Confirm all sources landing in Bronze | Verify every one of the 7 sources is landing in the DEV Bronze lakehouse on its expected cadence before moving on to Silver/Gold work. | 0.5 | Data Engineer | 2.2, 2.3, 2.4 | Should
2.6 | Phase 2 | Compile Phase 2 deliverables package | Confirm working batch ingestion for all 5 batch sources and Eventstream ingestion for both streaming sources, all landing in DEV Bronze. | 0.5 | All | 2.5 | Should
3.1 | Phase 3 | Build Silver-layer notebooks/pipelines | Cleanse, conform types, deduplicate, and standardize (timestamps, codes); apply referential integrity checks across patients, staff, facilities, drugs. | 2 | Data Engineer | 2.5 | Must
3.2 | Phase 3 | Implement data quality framework | Implement the documented data quality framework between Silver and Gold: completeness, validity, uniqueness, referential integrity, and freshness checks, with visible pass/fail results (not just spot-checks). | 1.5 | Data Engineer | 3.1 | Must
3.3 | Phase 3 | Build Gold facts/dimensions and derive KPIs | Build Gold-layer facts and dimensions per the Phase 1 data model, and derive the KPIs as Gold-layer measures or curated tables feeding the Power BI semantic model. | 2 | Data Engineer | 3.1 | Must
3.4 | Phase 3 | Compile Phase 3 deliverables package | Confirm Silver and Gold lakehouses populated end-to-end for at least one full batch cycle plus a running window of streaming data, with documented DQ check results. | 0.5 | All | 3.2, 3.3 | Should
4.1 | Phase 4 | Orchestrate full pipeline in Data Factory | Orchestrate batch pipelines on their real-world cadence (daily/weekly/intraday) and a scheduled/continuous path for streaming consumption, with dependencies between Bronze -> Silver -> Gold stages. | 2 | Data Engineer | 3.3 | Must
4.2 | Phase 4 | Add monitoring/alerting | Add monitoring/alerting on pipeline failure and on data quality check failures. | 1 | Platform Engineer | 4.1 | Must
4.3 | Phase 4 | Start Power BI semantic model & Executive Dashboard | Begin building the Power BI semantic model on top of Gold, and start the Executive Dashboard: network-wide KPIs, trends, executive summary. | 2 | BI Developer | 3.3 | Must
4.4 | Phase 4 | Compile Phase 4 deliverables package | Confirm the end-to-end orchestrated pipeline with monitoring, and a first working draft of the Executive Dashboard. | 0.5 | All | 4.2, 4.3 | Should
5.1 | Phase 5 | Complete Operational/Clinical Dashboard | Complete facility/department/shift-level detail, drill-down from executive KPIs, and exception views (capacity risk, understaffed shifts, stockout risk, elevated critical-alert rates). | 2 | BI Developer | 4.3 | Must
5.2 | Phase 5 | Test the full pipeline end-to-end | Simulate a full batch cycle for every source, run the streaming producers long enough to validate Eventstream behavior, and deliberately break something (bad row, late file, stream gap) to confirm data quality checks and monitoring actually catch it. | 1.5 | Data Engineer | 4.1, 4.2 | Must
5.3 | Phase 5 | Validate against success criteria | Walk through client-request.md Section 4 (Success Criteria) line by line and validate the platform against each one; fix gaps. | 1 | All | 5.1, 5.2 | Must
5.4 | Phase 5 | Compile Phase 5 deliverables package | Confirm both dashboards complete, test results documented, and a completed success-criteria validation checklist. | 0.5 | All | 5.3 | Should
6.1 | Phase 6 | Promote DEV -> UAT -> PROD | Use Fabric deployment pipelines to promote workspace content DEV -> UAT -> PROD; validate that PROD reflects a tested, promoted state rather than direct edits. | 1 | Platform Engineer | 5.3 | Must
6.2 | Phase 6 | Finalize documentation | Finalize architecture, data model, and governance/access documentation (including how PII/PHI fields are protected per audience), plus an operational runbook for running/monitoring the pipelines. | 1.5 | All | 6.1 | Must
6.3 | Phase 6 | Prepare and deliver final presentation | Prepare and deliver the final presentation: architecture, KPIs answered, both dashboards, and how the platform meets the client's success criteria. | 1 | All | 6.2 | Must
6.4 | Phase 6 | Compile Phase 6 deliverables package | Confirm the promoted PROD workspace via deployment pipelines, the final documentation package, and the final presentation are all complete. | 0.5 | All | 6.3 | Should